## Sheet1
| WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11
Tasks | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 2020-11-29 | 2020-11-30 | 2020-12-01 | 2020-12-02 | 2020-12-03
Assign a project manager | 10 min
Roles Assignment | 20 min
Discussion on the topic of 1st meeting | 2 hours
Create and beautify the sildes | [10 empty] | 1 hour
Deliver the sildes for the 1st meeting | [10 empty] | 10 min
Arrange tasks for each person for the 1st meeting | [10 empty] | 30 min
Meet with our instructor (1st meeting) | [11 empty] | 1 hour
Discussion on the pipline of the project | [11 empty] | 1 hour 30 min | 1 hour
Check data source and accessibility |  | Legend | [9 empty] | 1 hour 30 min | 1 hour 30 min
Create and deliver the sildes for the 2nd meeting |  | Milestone | [15 empty] | 1 hour
Arrange tasks for each person for the 2nd meeting |  | Deliverable | [15 empty] | 30 min
Meet with our instructor (2nd meeting) | [18 empty] | 3
Prepare to execute the project
Assign the sub-group and their tasks of the project
Find optimal training dataset and its time period on different models
Find a member to train the CNN model | [30 empty] | 10 min
Record and check the performance of LR models | [30 empty] | 3 hours | 1 hour | 3 hours | 1 hour | 2 hours | 2 hours | 3 hours | 1 hour | 2 hours | 3 hours | 2 hours | 1 hour | [6 empty] | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour |  |  | 3 hours | 3 hours | 3 hours | 3 hours | 2 hours | 2 hours
Tune parameters of the CNN model and check its performance | [30 empty] | 3 hours | 3 hours | 3 hours | 1 hour | 1 hour | 3 hours | 4 hours | 4 hours | 2 hours | 3 hours | 3 hours | 1 hour |  |  |  | 3 hours | 3 hours | 1 hour | 1 hour | 3 hours | 3 hours | 1 hour | 1 hour | 1 hour |  |  | 4 hours | 4 hours | 4 hours | 4 hours | 2 hours | 3 hours
Resolve Datetime format error | [32 empty] | 1 hour
Prepare for the 3rd meeting | [41 empty] | 2 hour 30 min
Meet with our instructor (3rd meeting) | [42 empty] | 1 hour
Assign a person to do the reforcast data | [42 empty] | 30 min
Download and analyze the reforcast data | [43 empty] | 3 hours | 3 hours | 3 hours | 3 hours | 1 hour | 1 hour | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 1 hour
Prepare for the 4th meeting | [46 empty] | 1 hour | 1 hour | 30 min
Meet with our instructor (4th Meeting) | [49 empty] | 1 hour
Create a figshare and put experimental results | [51 empty] | 1 hour | 3 hours | 2 hours | 2 hours | 2 hours
Prepare for the rehearsal and record the video | [51 empty] | 2 hours | 1 hour | 1 hour | 2 hours | 2 hours
Doing the comparison by using reforecast data | [56 empty] | 2 hours | 2 hours | 2 hours | 1 hour 30min | 30 min
Deliver the rehearsal video | [56 empty] | 2 hours
Data and software management | [58 empty] | 1 hour 30min | 1 hour 30min | 2 hours | 2 hours | 2 hours
Prepare for the final meeting and record the video | [57 empty] | 1 hour | 30min | 1 hour 30min | 2 hours | 30min | 3 hours
Final meeting | [63 empty] | 2 hours
Put experimental results on figshare | [63 empty] | 1 hour | 1 hour | 1 hour | 2 hours | 1 hour | 1 hour | 1 hour
Test the code on different environment | [63 empty] | 1 hour | 2 hours
Assemble and publish the code | [64 empty] | 2 hours | 2 hours | 2 hours | 2 hours | 2 hours | 1 hour | 1 hour | 1 hour | 1 hour | 30 min | 30 min
Assign documentation tasks for each member | [59 empty] | 1 hour
Work on and revise the report | [60 empty] | 1 hour | 1 hour | 1 hour | 1 hour | 5 hours | 5 hours | 5 hours | 5 hours | 5 hours | 5 hours | 6 hours | 3 hours | 3 hours | 3 hours | 3 hours | 1 hour
Report submission | [75 empty] | 10 min